## Sheet1
Presentation Day |  | December 5th
| ETL |  | Machine Learnings |  |  |  |  | Web Page | [6 empty] | Administrative
| Data Cleanup From CSV | Standardizing Data | Logistic Regression + page | Decision Tree and Random Forest | SVM Model | KNN Method + page | Neural Network + page | Landing Page with One Data Page | Web Design/Lay Out | Introduction Stroke Page (information) | Data Page | Flask Server for Final Model | Prediction Page | About Page | Hosting of Web Site (where and how) | Down Select Winning Model | Presentation | Create Readme | Test WebPage | GitMaster
Jeanine | X | X | X |  |  |  |  | Sat 28th | Tues 24th | Sat 28th | Dec 1st | Sat 28th | Dec 1st | Dec 3rd | Sat 28th | Tues 24th | Dec 4th | Dec 4th | Dec 3rd
Vincent |  | X |  |  | X | X |  | Sat 28th | Tues 24th | Sat 28th | Dec 1st | Sat 28th | Dec 1st - Model integration | Dec 3rd | Sat 28th | Tues 24th | Dec 4th | Dec 4th | Dec 3rd | X
Emily |  | X |  | X |  |  |  | Sat 28th | Tues 24th | Sat 28th | Dec 1st | Sat 28th | Dec 1st (Web Page) | Dec 3rd | Sat 28th | Tues 24th | Dec 4th | Dec 4th | Dec 3rd
Jeff |  | X |  |  |  |  | X | Sat 28th | Tues 24th | Sat 28th | Dec 1st | Sat 28th | Dec 1st (Flask Connection to parts) | Dec 3rd | Sat 28th | Tues 24th | Dec 4th | Dec 4th | Dec 3rd